## Project Overview
SYSTEM TEST CASE TEMPLATE Version 1.0
GENERAL INFORMATION
Project Name | Generative AI Content Platform
Project Code | GACP-2026
Start Date | 26/01/2026
End Date | 13/03/2026
KEY MEMBERS
Project Manager | Phan Xuan Phuong Ngan
Business Analyst | Tran Ngoc Phuong Nghi
Project Technical Lead | Doan Phan Linh Nhi
QC Lead | Hoang Thi Minh Ngoc

## Revision
DOCUMENT REVISION HISTORY
No. | Version No. | Creation Date | Description | Author | Reviewed By Date | Approved By Date | Remarks
1 | 1 | 23/02/2026 | Initial creation of Test Case document | Phan Xuan Phuong Ngan | 24/02/2026 | 24/02/2026 | Initial
2 | 1.1 | 25/02/2026 | Added test cases for AI content generation feature | Phan Xuan Phuong Ngan | 26/02/2026 | 13/03/2026 | Added
3 | 1.2 | 25/02/2026 | Added test cases for Template & Brand feature | Hoang Thi Minh Ngoc | 26/02/2026 | 13/03/2026 | Added
4 | 1.3 | 25/02/2026 | Added test cases for SEO Optimizer feature | Tran Ngoc Phuong Nghi | 26/02/2026 | 13/03/2026 | Added
5 | 1.4 | 25/02/2026 | Added test cases for Collaboration & Approval feature | Doan Phan Linh Nhi | 26/02/2026 | 13/03/2026 | Added
CHECKLIST TEMPLATE REVISION HISTORY
No. | Version No. | Creation Date | Description | Author | Reviewed By Date | Approved By Date | Remarks
1 | 0.1 | 23/02/2026 | Initial checklist template | Phan Xuan Phuong Ngan | 24/02/2026 | 24/02/2026 | Initial
2
3
4
5

## Test Overall
SYSTEM TEST CASE OVERALL
No. | Sheet name | Latest Date of Test | Total Test case | Round 1 |  |  |  | Round 2 |  |  |  | Round 3 |  |  |  | Remarks
|  |  |  | Chrome |  | Edge |  | Chrome |  | Edge |  | Chrome |  | Edge
|  |  |  | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed | Passed | Failed
1 | Login | 03/03/2026 | 36 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 6 | 0
2 | Register | 03/03/2026 | 36 | 3 | 3 | 3 | 3 | 5 | 1 | 5 | 1 | 6 | 0 | 6 | 0
3 | AI Generator | 03/03/2026 | 78 | 6 | 7 | 6 | 7 | 12 | 1 | 12 | 1 | 13 | 0 | 13 | 0
4 | Template & Brand | 03/03/2026 | 96 | 14 | 2 | 13 | 3 | 16 | 0 | 16 | 0 | 16 | 0 | 16 | 0
5 | Seo Optimizer | 03/03/2026 | 168 | 23 | 5 | 23 | 5 | 27 | 1 | 27 | 1 | 28 | 0 | 28 | 0
6 | Collaboration | 03/03/2026 | 66 | 10 | 1 | 10 | 1 | 6 | 4 | 6 | 4 | 11 | 0 | 11 | 0
7 | Approval | 03/03/2026 | 66 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0
Total |  |  | 546 | 73 | 18 | 72 | 19 | 83 | 7 | 83 | 7 | 91 | 0 | 91 | 0

## Login
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Edge
Phan Xuan Phuong Ngan | 25/02/2026 |  | User Story 01 | ID-001~ID-0006 |  | PASSED | 6 | 6 | 6 | 6 | 6 | 6 | 36
[6 empty] | FAILED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 6 | 6 | 6 | 6 | 6 | 6 | 36
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | Authentication | Login | - Open [Login] screen | Verify user can login with valid account | 1. At Login screen - Enter valid Email - Enter valid Password 2. Click ""Login"" button | At step 2: - User login successfully - System navigates to [Home] screen | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-002 | Authentication | Login | - Open [Login] screen | Verify login fails when user enters incorrect password | 1. At Login screen - Enter valid Email - Enter incorrect Password 2. Click ""Login"" button | At step 2: - Login failed - Error message ""Invalid email or password. Please try again!"" will display | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-003 | Authentication | Login | - Open [Login] screen | Verify system shows validation when email field is empty | 1. At Login screen - Leave Email field empty - Enter Password 2. Click ""Login"" button | At step 2: - System shows validation message ""Please fill in all required fields."" | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-004 | Authentication | Login | - Open [Login] screen | Verify system shows validation when password field is empty | 1. At Login screen - Enter Email - Leave Password empty 2. Click ""Login"" button | At step 2: - System shows validation message ""Please fill in all required fields."" | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-005 | Navigation | Forgot Password Link | - Open [Login] screen | Verify user can navigate to [Forgot Password] screen | 1. At Login screen - Click ""Forgot password"" link 2. Check Forgot Password screen | At step 2: - System navigates to [Forgot Password] screen successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-006 | Navigation | Register Link | - Open [Login] screen | Verify user can navigate to [Register] screen | 1. At Login screen - Click ""Sign up"" link 2. Check Register screen | At step 2: - System navigates to [Register] screen successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 2026-03-03 | Phuong Ngan | Working as expected

## Register
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Edge
Phan Xuan Phuong Ngan | 25/02/2026 |  | User Story 02 | ID-001~ID-0006 |  | PASSED | 3 | 3 | 5 | 5 | 6 | 6 | 28
[6 empty] | FAILED | 3 | 3 | 1 | 1 | 0 | 0 | 8
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 6 | 6 | 6 | 6 | 6 | 6 | 36
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | Authentication | Register | - Open [Register] screen | Verify user can register with valid information | 1. At Register screen - Enter valid information 2. Click ""Register"" button | At step 2: - Account created successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-002 | Authentication | Register | - Open [Register] screen | Verify system shows error when email already exists | 1. At Register screen - Enter existing Email and other information 2. Click ""Register"" button | At step 2: - System displays message ""Email already exists"" | Failed | Failed | Bug-RGT-01 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-003 | Authentication | Register | - Open [Register] screen | Verify system shows error when password is less than 6 characters | 1. At Register screen - Enter other valid information - Enter Password less than 6 characters (ex: 12345) 2. Click ""Register"" button | At step 2: - System displays validation message ""Password must be at least 6 characters!"" | Failed | Failed | Bug-RGT-02 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-004 | Authentication | Register | - Open [Register] screen | Verify password confirmation mismatch | 1. At Register screen - Enter other valid information - Enter Password - Enter different Confirm Password 2. Click ""Register"" button | At step 2: - System displays message ""Passwords do not match. Please try again!"" | Failed | Failed | Bug-RGT-03 | 27/02/2026 | Phuong Ngan | Failed | Failed | Bug-RGT-04 | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-005 | Authentication | Register | - Open [Register] screen | Verify system shows error when required fields are empty | 1. At Register screen - Leave one of required fields empty (Name / Email Address / Password / Confirm Password) 2. Click ""Register"" button | At step 2: - System displays message ""Please fill in all required fields."" | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-006 | Navigation | Already have an account | - Open [Register] screen | Verify user can navigate to Login screen via ""Already have an account? Login Now!"" link | 1. At Register screen - Click ""Login Now!"" link 2. Check Login screen | At step 2: - System navigates to [Login] screen successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected

## AI Generator
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Edge
Phan Xuan Phuong Ngan | 25/02/2026 |  | User Story 03 | ID-001~ID-0013 |  | PASSED | 6 | 6 | 12 | 12 | 13 | 13 | 62
[6 empty] | FAILED | 7 | 7 | 1 | 1 | 0 | 0 | 16
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 13 | 13 | 13 | 13 | 13 | 13 | 78
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | UI/UX | Content Library View | - User already login successfully | Verify user can view generated contents in [AI Content Library] screen | 1. At Home screen - Click ""AI Generator"" menu 2. Check the list of generated contents | At step 2: - System displays list of generated contents successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-002 | Functionality | Content Detail | - User already open [AI Content Library] screen | Verify user can open a content item from library to see full content | 1. At AI Content Library screen - Click a content item from the list 2. Check content detail screen | At step 2: - System opens content detail successfully - Generated content is fully displayed | Failed | Failed | Bug-AI-01 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-003 | Functionality | Edit Content | - User already open [AI Content Library] screen | Verify user can edit content from AI Content Library | 1. At AI Content Library screen - Select a content item 2. Click ""Edit"" button | At step 2: - The content item is returned to the [AI Content Generator] screen for editing | Failed | Failed | Bug-AI-02 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-004 | Functionality | Delete Content | - User already open [AI Content Library] screen | Verify user can delete a content item from library | 1. At AI Content Library screen - Select a content item 2. Click ""Delete"" button | At step 2: - Content item is removed from AI Content Library successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-005 | Functionality | Search Content | - User already open [AI Content Library] screen | Verify user can search content in library | 1. At Content Library screen - Enter keyword in search bar | At step 1: - System displays contents matching the keyword | Failed | Failed | Bug-AI-03 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-006 | UI/UX | Content Filter | - User already open [AI Content Library] screen | Verify user can switch the filter between Blog, Post, and Email | 1. At AI Content Library screen - Select filter ""Blog"" - Change filter ""Post"" - Change filter ""Email"" | At step 1: - System generates content according to selected filter | Failed | Failed | Bug-AI-04 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-007 | Navigation | Create Content Navigation | - User already open [AI Content Library] screen | Verify user can navigate to AI Content Generator screen via ""Create Content"" button | 1. At Content Library screen - Click ""Create Content"" button 2. Check AI Content Generator screen | At step 2: - System navigates to [AI Content Generator] screen successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-008 | Functionality | Content Type Selection | - User already open [AI Content Generator] screen | Verify user can switch content type between Blog, Post, and Email | 1. At AI Content Generator screen - Select content type ""Blog"" - Change content type to ""Post"" - Change content type to ""Email"" | At step 1: - System generates content according to selected content type | Failed | Failed | Bug-AI-05 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-009 | Functionality | AI Content Generation | - User already open [AI Content Generator] screen | Verify AI can generate content from prompt | 1. At AI Content Generator screen - Select Content Type - Select Platform - Select Tone of Voice - Enter prompt into Topic or Prompt card 2. Click ""Generate AI Content"" button | At step 2: - AI content is generated successfully and displays into the right card | Failed | Failed | Bug-AI-06 | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-0010 | Functionality | Prompt Validation | - User already open [AI Content Generator] screen | Verify system validates empty prompt | 1. At AI Content Generator screen - Leave Prompt empty 2. Click ""Generate AI Content"" button | At step 2: - System displays validation alert message for prompt | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-0011 | Functionality | Copy Generated Content | - User already open [AI Content Generator] screen | Verify user can copy generated content | 1. At AI Content Generator screen - Select information and enter prompt - Click ""Generate AI Content"" button 2. Click ""Copy"" button | At step 2: - Generated content is copied successfully | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-0012 | Functionality | Regenerate Content | - User already open [AI Content Generator] screen | Verify user can regenerate content | 1. At AI Content Generator screen - Select information and enter prompt - Click ""Generate AI Content"" button 2. Click ""Regenerate"" button | At step 2: - System generates a new version of content | Passed | Passed | N/A | 27/02/2026 | Phuong Ngan | Passed | Passed | N/A | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected
ID-0013 | Functionality | Save Content to Library | - User already open [AI Content Generator] screen | Verify generated content can be saved | 1. At AI Content Generator screen - Select information and enter prompt - Click ""Generate AI Content"" button 2. Click ""Save to Library"" button | At step 2: - Generated content is saved to AI Content Library successfully | Failed | Failed | Bug-AI-07 | 27/02/2026 | Phuong Ngan | Failed | Failed | Bug-AI-07 | 01/03/2026 | Phuong Ngan | Passed | Passed | N/A | 03/03/2026 | Phuong Ngan | Working as expected

## Template & Brand
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Safari
Hoang Thi Minh Ngoc | 03/03/2026 |  | User Story 04 | ID-001~ID-0016 |  | PASSED | 14 | 13 | 16 | 16 | 16 | 16 | 91
[6 empty] | FAILED | 2 | 3 | 0 | 0 | 0 | 0 | 5
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 16 | 16 | 16 | 16 | 16 | 16 | 96
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Safari | Bug ID
ID-001 | UI/UX | Templates Screen | User logged in | Verify the UI of Templates screen is correct with design | 1. Open [Templates & Brand] screen 2. Check the UI of Templates screen | At step 2: - UI of "Templates" screen is correct with design | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-002 | Navigation | Switch Tab | At "Templates" tab | Verify user can switch to Brand Guide tab | 1. Open [Templates & Brand] screen 2. Click on "Brand Guide" tab | At step 2: - Templates" section is hidden. "Brand Guide" section is displayed. | Failed | Failed | BUG-TB-01 | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-003 | Functionality | Filter Templates | At "Templates" tab | Verify user can filter templates by category | 1. Open [Templates & Brand] screen 2. Click Blog, Post, or Email filter | At step 2: - Templates displayed correspond to the selected category | Passed | Failed | BUG-TB-02 | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-004 | UI/UX | Use Button Display | User on Template page | Verify "Use" button appears when hovering over a template | 1. Open [Templates & Brand] screen 2. Hover the mouse over any template | At step 2: - "Use" button appears | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-005 | Functionality | Open Template popup | User on Template page | Verify popup opens when clicking Use | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use | At step 3: - Template popup is displayed | Failed | Failed | BUG-TB-03 | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-006 | Functionality | Input Content | Popup opened | Verify user can enter content in the template fields | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use 4. Enter content into fields | At step 4: - Content is displayed | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-007 | Functionality | Copy content | Popup opened with content | Verify user can copy generated content | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use 4. Enter content 5. Click Copy | At step 5: - Content is copied to clipboard - Display message "Content copied to clipboard!" | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-008 | Functionality | Download content | Popup opened with content | Verify user can download generated content | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use 4. Enter content 5. Click Download | At step 5: - File downloads successfully - Display message "Successfully exported." | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-009 | Popup | Delete content | Popup opened with content | Verify user can delete content | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use 4. Enter content 5. Click Delete | At step 5: - Content is removed from fields - Display message "All content has been deleted." | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0010 | Popup | Close popup | Template popup opened | Verify popup closes when clicking X | 1. Open [Templates & Brand] screen 2. Hover template 3. Click Use 4. Click X icon | At step 4: - Popup closes and user returns to Template page | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0011 | Navigation | Open Brand Guide | User logged in and on Template & Brand page | Verify user can open Brand Guide tab | 1. Open [Templates & Brand] screen 2. Click Brand Guide tab | At step 2: - Brand Guide screen is displayed | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0012 | Functionality | Edit Brand Name | Brand Guide screen opened | Verify user can edit brand name | 1. Open [Templates & Brand] screen 2. Click Brand Guide tab 3. Enter new brand name | At step 3: - Brand name is updated in the field | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0013 | Functionality | Edit Slogan | Brand Guide screen opened | Verify user can edit slogan | 1. Open [Templates & Brand] screen 2. Click Brand Guide tab 3. Enter slogan text | At step 3: - Slogan is displayed in the field | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0014 | Functionality | Select Tone of Voice | Brand Guide screen opened | Verify user can select tone of voice | 1. Open [Templates & Brand] screen 2. Click Brand Guide tab 3. Click one tone option (Friendly / Bold / Professional...) | At step 3: - Selected tone is highlighted | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0015 | UI/UX | Typography Display | Brand Guide screen opened | Verify typography settings are displayed | 1. Open [Templates & Brand] screen 2. Click Brand Guide tab 3. View typography section | At step 3: - Typography information is displayed correctly | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected
ID-0016 | Functionality | Save Changes | User edited brand information | Verify user can save brand guide changes | 1. Open [Templates & Brand] screen 2. Edit brand information 3. Click Save changes | At step 3: - Changes are saved successfully | Passed | Passed | N/A | 27/02/2026 | Minh Ngoc | Passed | Passed | N/A | 01/3/2026 | Minh Ngoc | Passed | Passed | N/A | 03/3/2026 | Minh Ngoc | Working as expected

## SEO Optimizer
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Platform 1 | Platform 2 | Platform 1 | Platform 2 | Platform 1 | Platform 2
Tran Ngoc Phuong Nghi | 25/02/2026 |  | User Story 05 | ID-001~ID-0028 |  | PASSED | 23 | 23 | 27 | 27 | 28 | 28 | 156
[6 empty] | FAILED | 5 | 5 | 1 | 1 | 0 | 0 | 12
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 28 | 28 | 28 | 28 | 28 | 28 | 168
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | UI/UX | Layout and Display | User logged in, navigates to SEO Optimizer | Verify all UI elements are displayed correctly | 1. Navigate to SEO Optimizer from sidebar. 2. Observe: Header, Article Name field, Content Editor, Back button, Analyze Content button. | All elements are visible and properly aligned as per design. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-002 | Functionality | Article Name Input | User is on Content Analysis screen | Verify Article Name field accepts text input | 1. Click Article Name input. 2. Type: 'Best Travel Destinations in Vietnam 2025' 3. Verify text displays correctly. | Text is accepted and displayed correctly in the field. | Failed | Failed | BUG-SEO-01 | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-003 | Functionality | Content Editor | User is on Content Analysis screen | Verify Content Editor accepts pasted/typed content | 1. Click on Content Editor. 2. Paste a draft article (>20 words). 3. Verify content fully displayed. | All content is displayed correctly without truncation. | Failed | Failed | BUG-SEO-02 | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-004 | Functionality | Analyze Content Button | Article Name and Content Editor are filled | Verify Analyze Content button navigates to SEO Settings screen | 1. Enter valid title and content. 2. Click 'Analyze Content'. | System navigates to SEO Settings screen (SEO Optimization Settings). | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-005 | Functionality | Back Button | User is on Content Analysis screen | Verify Back button returns to previous screen | 1. Click 'Back' button in footer. | User is navigated back to the previous screen. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-006 | UI/UX | Layout & Display | User arrives from Content Analysis screen | Verify all elements on SEO Optimization Settings screen are displayed | 1. Complete Content Analysis screen and click Analyze Content. 2. Check: Article Name, Summary Badges, Content Structure Panel, Primary Keyword, Additional Keywords, Content Type, Target Word Count, Back/Analyze buttons. | All elements visible. Article Name carries over from Content Analysis screen. Badges show word count and heading count. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-007 | Functionality | Content Summary Badges | User is on SEO Settings screen with content loaded | Verify badges display accurate word count and heading count | 1. Check word count badge vs actual word count. 2. Check heading count badge vs actual headings (H1/H2/H3). | Word count and heading count badges match the submitted content. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-008 | Functionality | Primary Keyword | User is on SEO Settings screen | Verify Primary Keyword field accepts input | 1. Click Primary Keyword field. 2. Type 'destination'. 3. Verify text saved and displayed. | Primary keyword is accepted and displayed correctly. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-009 | Functionality | Add Keyword Field | User is on SEO Settings screen | Verify user can add custom keywords | 1. Click Add Keyword input. 2. Type 'on-page optimization'. 3. Press Enter or click Add. 4. Verify keyword appears in list. | New keyword is added and displayed in Additional Keywords list. | Failed | Failed | BUG-SEO-03 | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0010 | Functionality | Content Type Dropdown | User is on SEO Settings screen | Verify Content Type dropdown shows correct options | 1. Click Content Type dropdown. 2. Observe options (Blog, Email, Post). 3. Select 'Blog'. 4. Verify selection saved. | Dropdown shows Blog, Email, Post. Selected value displayed correctly. | Failed | Failed | BUG-SEO-04 | 27/02/2026 | Phuong Nghi | Failed | Failed | BUG-SEO-06 | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0011 | Functionality | Analyze Content Button | Required settings configured on SEO Settings screen | Verify Analyze Content button proceeds to SEO Research screen | 1. Fill Primary Keyword and select Content Type. 2. Click 'Analyze Content'. | System navigates to SEO Research screen | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0012 | Functionality | Back Button | User is on SEO Settings screen | Verify Back button returns to Content Analysis screen | 1. Click 'Back' button. | User returns to Content Analysis screen. Article name and content are preserved. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0013 | UI/UX | Layout & Display | User arrives from SEO Settings screen | Verify all UI elements on SEO Research screen are displayed | 1. Complete SEO Settings screen and click Analyze Content. 2. Check: Tabs (Research/Outline), Progress Indicator, Analyzing Intent section, Expanding Keywords section, Back/Optimize buttons. | All elements visible. 'Research' tab is active. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0014 | Functionality | Analyzing Intent | Analysis is complete | Verify search intent is classified and displayed | 1. After analysis, observe Search Intent Type. 2. Check intent label (Informational / Transactional / Navigational). | Search intent type is classified and displayed with label and explanation. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0015 | Functionality | Expanding Keywords | Analysis is complete | Verify Expanding Keywords shows related keywords with CPC and coverage | 1. Observe Expanding Keywords section. 2. Verify each keyword shows: keyword text, CPC value, content coverage %. | At least 5 related keywords displayed with CPC and content coverage metrics. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0016 | Functionality | Optimize Content Button | Research is complete | Verify Optimize Content button navigates to Optimized Outline Screen | 1. Click 'Optimize Content' button. | User navigated to Optimized Outline Screen | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0017 | Functionality | Back Button | User is on SEO Research screen | Verify Back button returns to SEO Settings screen | 1. Click 'Back' button. | User returns to SEO Settings screen with previous settings preserved. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0018 | UI/UX | Layout & Display | User arrives from SEO Research screen | Verify all UI elements on Optimized Outline screen are displayed | 1. Navigate from SEO Research screen. 2. Check: Tabs (Research/Outline), Target Keywords section, Optimized Outline section, Back/Optimize buttons. | All elements visible. 'Outline' tab is active. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0019 | Functionality | Target Keywords Section | Analysis and research are complete | Verify Target Keywords shows keywords with heading level and search volume | 1. Observe Target Keywords section. 2. Verify each keyword shows: text, heading level (H1/H2/H3), search volume. | At least 3 target keywords displayed with heading level and search volume. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0020 | Functionality | Optimized Outline | User is on Optimized Outline Screen | Verify AI-generated outline is displayed with correct hierarchy | 1. Observe Optimized Outline section. 2. Verify structured headings H1 > H2 > H3 based on selected keywords. | Outline displayed with clear H1 > H2 > H3 hierarchy based on research results. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0021 | Functionality | Optimize Content Button | User reviewed the outline | Verify Optimize Content button navigates to Screen 5 | 1. Click 'Optimize Content' button. | User navigated to Screen 5 (Edit Article). | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0022 | Functionality | Back Button | User is on Optimized Outline Screen | Verify Back button returns to SEO Research screen | 1. Click 'Back' button. | User returns to SEO Research screen (SEO Research) with results preserved. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0023 | UI/UX | Layout & Display | User arrives from Optimized Outline Screen | Verify all UI elements on Edit Article screen are displayed | 1. Navigate from Optimized Outline Screen. 2. Check: Article Title input, Content Editor, Word Count, Quality Scores Panel, Improve button, Rewrite button, Submit button. | All elements visible. AI-generated article pre-populated in Content Editor. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0024 | Functionality | Content Editor | Article content is pre-populated | Verify Content Editor allows manual editing | 1. Click inside Content Editor. 2. Modify a paragraph (add/delete/change text). 3. Verify changes reflected immediately. | All edits reflected in real time without data loss. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0025 | Functionality | Quality Scores Panel | Article content is loaded | Verify Quality Scores Panel shows SEO score and content quality metrics | 1. Observe Quality Scores Panel. 2. Check SEO Score and Content Quality values. 3. Edit content and verify scores update. | SEO score and content quality metrics displayed and update after content changes. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0026 | Functionality | Improve Button | Content is loaded in editor | Verify Improve button enhances content without full rewrite | 1. Click 'Improve' button. 2. Observe changes in Content Editor. 3. Verify structure is maintained. | Content improved (better phrasing/SEO) without complete rewrite. Loading indicator shown during processing. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0027 | Functionality | Rewrite Button | Content is loaded in editor | Verify Rewrite button generates new SEO-optimized version | 1. Click 'Rewrite' button. 2. Observe new content generated. 3. Compare with original. | New article content generated with stronger SEO. Loading indicator shown. Original replaced or comparison view shown. | Passed | Passed | N/A | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected
ID-0028 | Functionality | Submit for Approval | Article content is finalized | Verify Submit for Approval button submits content correctly | 1. Click the Submit for Approval button in footer. 2. Observe system response. | Content submitted successfully. Success message shown or user redirected to Approval module. | Failed | Failed | BUG-SEO-05 | 27/02/2026 | Phuong Nghi | Passed | Passed | N/A | 01/3/2026 | Phuong Nghi | Passed | Passed | N/A | 3/03/2026 | Phuong Nghi | Working as expected

## Collaboration
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Edge
Doan Phan Linh Nhi | 25/02/2026 |  | User Story 06 | ID-001~ID-0011 |  | PASSED | 10 | 10 | 6 | 6 | 11 | 11 | 54
[6 empty] | FAILED | 1 | 1 | 4 | 4 | 0 | 0 | 10
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 11 | 11 | 11 | 11 | 11 | 11 | 66
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | UI/UX | Collaboration Page Layout | User logged into system | Verify all UI elements of Collaboration page display correctly | 1. Login to the system 2. Click Collaboration on sidebar 3. Observe page layout | Team Members section, Search bar, Invite Member button, and Recent Activity section are displayed correctly | Failed | Failed | BUG-COL-01 | 27/02/2026 | Linh Nhi | Failed | Failed | BUG-COL-01 | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-002 | Functionality | Invite Member Button | User is on Collaboration page | Verify Invite Member button opens invite form | 1. Navigate to Collaboration page 2. Click Invite Member | Invite Member popup/modal is displayed | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-003 | Functionality | Search Team Member | Team members exist | Verify search bar filters team members | 1. Navigate to Collaboration page 2. Enter a member name in search bar | System displays matching members | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Failed | Failed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-004 | UI/UX | Role Badge Display | Team members exist | Verify role badge (Admin/Member) is displayed | 1. Open Collaboration page 2. Observe member | Each member shows the correct role badge | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Failed | Failed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-005 | UI/UX | Member Information Display | Team members exist | Verify member card displays correct information | 1. Open Collaboration page | Member avatar, name, email, and content count are displayed correctly | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-006 | UI/UX | Recent Activity Display | System contains activity logs | Verify Recent Activity section displays activity logs | 1. Navigate to Collaboration page 2. Scroll to Recent Activity section | Activity list shows user action, content title, and timestamp | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-007 | Functionality | Email Input | Invite Member form is open | Verify email input accepts valid email | 1. Open Invite Member form 2. Enter email: user@example.com | Email is accepted and displayed correctly | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-008 | Validation | Invalid Email | Invite Member form is open | Verify system shows error for invalid email | 1. Enter email: abc123 2. Click Invite | System displays validation message for invalid email | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Failed | Failed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-009 | Functionality | Role Selection | Invite Member form is open | Verify user can select role from dropdown | 1. Click Role dropdown 2. Select Member | Selected role is displayed in dropdown | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-0010 | Functionality | Invite Member Button | Email entered and role selected | Verify invitation is sent successfully | 1. Enter valid email 2. Select role 3. Click Invite | System sends invitation successfully | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Passed | Passed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi
ID-0011 | Functionality | Cancel Button | Invite Member form is open | Verify Cancel button closes invite form | 1. Click Cancel button | Invite Member form closes | Passed | Passed | N/A | 27/02/2026 | Linh Nhi | Failed | Failed | N/A | 01/03/2026 | Linh Nhi | Passed | Passed | N/A | 03/03/2026 | Linh Nhi

## Approval
SYSTEM TEST CASE
[7 empty] | Round 1 |  | Round 2 |  | Round 3 |  | SUM
Author | Modified Date |  | SRS/ User Stories ID | Test case ID Range |  |  | Chrome | Edge | Chrome | Edge | Chrome | Edge
Doan Phan Linh Nhi | 25/02/2026 |  | User Story 07 | ID-001~ID-0011 |  | PASSED | 11 | 11 | 11 | 11 | 11 | 11 | 66
[6 empty] | FAILED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | BLOCKED | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | NOT RUN | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Number of Test case | 11 | 11 | 11 | 11 | 11 | 11 | 66
No. | Main Category | Sub Category | Pre-conditions | Test Description | Steps to Perform (include Data test) | Expected Results | Round 1 |  |  |  |  | Round 2 |  |  |  |  | Round 3 |  |  |  |  | Remarks
[7 empty] | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked | Testing result |  |  | Result Recorded Date | Who checked
[7 empty] | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID |  |  | Chrome | Edge | Bug ID
ID-001 | UI/UX | Approval Page Layout | User logged into system | Verify Approval Workflow page displays all UI elements correctly | 1. Login to system 2. Click Approval on sidebar | Approval statistics, Approval Queue, filter tabs, and content list are displayed correctly | Passed | Passed | N/A | 02/03/2026 | Linh Nhi | Passed | Passed | N/A | 07/03/2026 | Linh Nhi | Passed | Passed | N/A | 12/03/2026 | Linh Nhi
ID-002 | UI/UX | Approval Statistics | Approval page opened | Verify statistics cards display correct numbers | 1. Navigate to Approval page 2. Observe Pending Review, Approved, Rejected cards | Statistics cards show correct counts | Passed | Passed | N/A | 02/03/2026 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-003 | Functionality | Filter Tabs | Content items exist | Verify filter tabs filter content list | 1. Open Approval page 2. Click Pending tab 3. Click Reviewed tab | Content list updates based on selected filter | Passed | Passed | N/A | 02/03/2026 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-004 | UI/UX | Content Item Display | Content items exist | Verify content item displays correct information | 1. Open Approval page 2. Observe content items | Each item shows title, author, timestamp, and status badge | Passed | Passed | N/A | 02/03/2026 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-005 | Functionality | Review Button | Content item status = Pending Review | Verify Review button opens review modal | 1. Navigate to Approval page 2. Click Review button | Review modal is displayed | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-006 | Functionality | Approve Content | Review modal opened | Verify reviewer can approve content | 1. Click Approve button | Content status changes to Approved | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-007 | Functionality | Reject Content | Review modal opened | Verify reviewer can reject content | 1. Click Reject button | Content status changes to Rejected | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-008 | UI/UX | Status Badge Display | Content items exist | Verify status badge displays correct color and label | 1. Open Approval page | Pending Review, Approved, and Rejected badges are displayed correctly | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-009 | Functionality | Approved Content Display | Some content already approved | Verify approved content appears correctly in list | 1. Navigate to Approval page | Approved content shows Approved status badge | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-0010 | Functionality | Rejected Content Display | Some content already rejected | Verify rejected content appears correctly | 1. Navigate to Approval page | Rejected content shows Rejected badge | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi
ID-0011 | UI/UX | Review Modal Layout | Review modal opened | Verify review modal displays correct layout | 1. Click Review button | Modal shows content title, Approve button, and Reject button | Passed | Passed | N/A | 2026-02-03 | Linh Nhi | Passed | Passed | N/A | 2026-07-03 | Linh Nhi | Passed | Passed | N/A | 2026-12-03 | Linh Nhi

## Instruction
INSTRUCTION
This sheet is to describe/explain how to input/update in fields of the template
No. | Title | Instruction | Remarks
1 | No. | 1 | Ex: 1, 2, 3, 4
2 | PM | Project Manager
3 | BA | Business Analyst
4 | QC | Quality Control
5 | Ver. | 1.0 version | Ex: 1.2, 1.3
6 | SRS/ User Stories ID | Software requirements specification/ User Stories No. Related to test cases, which just updated | Ex: User Story 01
7 | Test case ID Range | For each software requirements specification/ User Stories No., some test cases are added. List id of them on this field. | Ex: Add TC 1 ~ 14 for User Story 01, so, input "ID-001~ID-0014" in this field.
8 | Date, Creation Date | 13/03/2026 | Ex: 10/03/2026
9 | Latest Date of Test | 14/03/2026 | Ex: Testing in a week (from 09/20/2017 to 09/26/2017), fill "09/26/2017" in this field.
10 | Platform | Google Chrome Microsoft Edge | Ex: 1. Google Chrome Version 60.0.3112.113 on Windows 2. Microsoft Edge
11 | Main Category | AI Content Generation | Ex: category "Admin"
12 | Sub Category | Generate Article | Ex: In category "Admin", has some sub-category: Users information, Reporter information.
13 | Pre-conditions | User logged in successfully | Ex: Login successfully prior to Edit profile. So, in Pre-conditions field, input "Login successfully".
14 | Test Description | Verify the system can generate article content using AI
15 | Steps to Perform (include Data test) | Step-by-step procedure to execute the test (include data information needed to execute the test).
16 | Expected Results | The system generates a complete article
17 | Testing result | Passed | Ex: The actual result is same with expected result, fill "Passed".
18 | Result Recorded Date | The date of execution of the test. Format is dd/mm/yyyy | Ex: 10/03/2026
19 | Who checked | The name of the tester who executed the test case.
20 | Remarks | Any comments on the test case or test execution, such as known issues, environment notes, or reasons for being blocked.
21 | Bug ID | The ID of the bug logged when a test case result is Failed or Blocked.